## SHOPPEE
Date | Task Name | Done by | Inputs | Experiment | Model name | Baseline | Run_time | Run_Status | F1_Score | SOURCE
2021-04-01 | Project setup | Team | 1.91 GB shopee-product-matching timm-pytorch-image-models utils-shopee
2-April-2021 : 5-April-2021 | EDA & Preprocessing | Sudha Vijayakumar | 1.91 GB shopee-product-matching | Understanding data & Preprocessing |  |  |  | Success | NA | https://www.kaggle.com/sudhavijayakumar/understanding-the-problem-eda-phase-algo-nlp
2-April-2021 : 5-April-2021 | EDA & Preprocessing | Akash Aggarwal | 1.91 GB shopee-product-matching | Understanding data & Preprocessing |  |  |  | Success | NA
2-April-2021 : 5-April-2021 | EDA & Preprocessing | Sowmya Mruthyunjaya | 1.91 GB shopee-product-matching | Understanding data & Preprocessing |  |  |  | Success | NA
2-April-2021 : 5-April-2021 | Match by pHash | Team | 1.91 GB shopee-product-matching | Phash matching Algorithm | Phash matching |  |  | Success | NA | https://www.kaggle.com/sudhavijayakumar/understanding-the-problem-eda-phase-algo-nlp
5-April-2021 : 7-April-2021 | Training & Prediction | Sowmya Mruthyunjaya | 1.91 GB shopee-product-matching | Predict matches using resnet152 + TFDIF | resnet152 |  |  | Success | NA | https://www.kaggle.com/sudhavijayakumar/resnet152-tfdif?scriptVersionId=60612777
5-April-2021 : 7-April-2021 | Training & Prediction | Sudha Vijayakumar | [Model] Pytorch + [Preprocessed data] Utils Shopee preprocessed data | Trained for 10 epochs | EffNet3 | TRUE |  |  | 0.723
7-April-2021 : 9-April-2021 | Training | Sudha Vijayakumar | [Model] Pytorch + [Preprocessed data] Utils Shopee preprocessed data | Baseline: 10 epochs Task: Effnet for 12 epochs | EffNet3 |  | ~10 hours | Success |  | https://colab.research.google.com/drive/1JewsKZS2FkN8jJ70O63QDtLLe__CybUF?authuser=1#scrollTo=Ip2rC61p3KLb
9-April-2021 : 11-April-2021 | Training | Sudha Vijayakumar | [Model] Pytorch + [Preprocessed data] Utils Shopee preprocessed data | Baseline: 10 epochs Task: Effnet for 12 epochs | EffNet5 |  | ~15 hours | Success |  | https://colab.research.google.com/drive/1JewsKZS2FkN8jJ70O63QDtLLe__CybUF?authuser=1#scrollTo=Ip2rC61p3KLb
11-April-2021 : 13-April-2021 | Training | Sudha Vijayakumar | [Model] Pytorch + [Preprocessed data] Utils Shopee preprocessed data | Task: To train Effnet6 for 20 epochs | EffNet6 |  | ~34 hours | Success |  | https://colab.research.google.com/drive/1JewsKZS2FkN8jJ70O63QDtLLe__CybUF?authuser=1#scrollTo=Ip2rC61p3KLb
11-April-2021 : 13-April-2021 | Prediction | Sudha Vijayakumar | [Model] Pytorch + [Preprocessed data] Utils Shopee preprocessed data | Task: To make predictions using EffNet | EffNet6 |  |  | Success | 0.73 | https://www.kaggle.com/sudhavijayakumar/efficientnet-b-3-5-6-image-tfidf
14-April-2021 : Ongoing | Training | Sudha Vijayakumar | [Model] Pytorch + [Preprocessed data] Utils Shopee preprocessed data | Task: To find similar images using fastai | fastai + Annoy |  |  | In Progress
9-April-2021 : 11-April-2021 | Training | Akash Aggarwal |  | Task: To train eca_nffnet-10 for 3 epochs | eca-nfnet-l0 |  | -2hrs | success | not submitted | https://www.kaggle.com/parthdhameliya77/pytorch-eca-nfnet-l0-image-tfidf-inference/data?select=arcface_512x512_nfnet_l0.pt
12-April-2021 : 15-April-2021 | Training | Akash Aggarwal |  | Task: To train eca_nffnet-10 for 6 epochs | eca-nfnet-l0 |  | -8hrs | success | not submitted | https://www.kaggle.com/parthdhameliya77/pytorch-eca-nfnet-l0-image-tfidf-inference/data?select=arcface_512x512_nfnet_l0.pt
16-April-2021 : 18-April-2021 | Training | Akash Aggarwal |  | Task: To train resnet50 | resnet50 |  |  | success | 0.62 | https://www.kaggle.com/karthur10/resnet-sbert-unsupervised-baseline
18-April-2021 : Ongoing | Training | Akash Aggarwal |  | https://www.kaggle.com/prashantkikani/shopee-ensemble-of-multiple-models/data | ensemble learning |  |  | minor errors |  | https://www.kaggle.com/akash15o3/shopee-ensemble-of-multiple-models/edit
4/17/2021: | Finding similar images using ImagedUp library | Sowmya Mruthyunjaya |  | https://www.kaggle.com/heyytanay/finding-similar-images-using-image-deduplicator | Trial |  |  | Succeded. Unsure at this point if we will use it for final submission | No submission needed for this at this point of time. | https://www.kaggle.com/heyytanay/finding-similar-images-using-image-deduplicator
20-April-2021: Ongoing | Generate tfrecord for the images and train rensnet152 | Sowmya Mruthyunjaya |  | https://www.kaggle.com/lhagiimn/shopee-tf-with-tpu-256x256-tfrecs | Transfer learning | Trying resnet152 from tensorflow model zoo to find duplicates. |  | WIP | Not submitted. | https://www.kaggle.com/lhagiimn/shopee-tf-with-tpu-256x256-tfrecs
Ongoing | Prediction | Team |  | Task: To ensemble best performing models and make predictions | Ensemble |  |  |  | Not submitted. | https://www.kaggle.com/sudhavijayakumar/shopee-ensemble-b6-nfnet-l0-inference